## Sheet1
ISSUE # | CREATION DATE | CREATED BY | DESCRIPTION | DATE CLOSED | CLOSED BY | DESCRIPTION OF CHANGES
1 | 2024-10-26 | Khiem | Folding mechanism required manual one-hand operation with a traditional fold design. | 2024-11-10 | Khiem | Replaced with a single-button automatic folding mechanism where the vertical support bar collapses downward, simplifying one-handed folding.
2 | 2024-10-27 | Khiem | Initial design used a standard convertible seat that required manual adjustment for child size. | 2024-11-10 | Khiem | Updated to an ergonomic, egg-shaped seating pod with modular seat adjustments and shock absorption, ensuring stability and comfort on rough terrain.
3 | 2024-10-29 | Khiem | Stroller required manual push, with no assistance for navigating difficult terrain or crowded areas. | 2024-11-10 | Khiem | Added motorized assistance to reduce physical effort, allowing smooth movement on sidewalks and inclines with minimal strain.
4 | 2024-10-30 | Khiem | Initial design lacked specific weatherproof and shock-absorbing features, limiting usage on uneven or wet city streets. | 2024-11-10 | Khiem | Integrated weather-resistant materials and shock-absorbing base for smooth and stable movement over varied city surfaces, including wet or bumpy roads.
5 | 2024-10-31 | Khiem | Stroller design focused on traditional storage compartments, requiring manual reach and handling. | 2024-11-10 | Khiem | Replaced with a compact under-seat storage compartment with easy access, ensuring essential items remain secure and accessible with one hand.
6 | 2024-11-03 | Khiem | Brake system offered a traditional hand or foot brake for stopping. | 2024-11-10 | Khiem | Enhanced with a smart brake system with audio feedback to confirm brake engagement, supporting visual impairments and adding reassurance.
7 | 2024-11-05 | Khiem | Required sight-based use of handlebar controls, which may have been challenging for visually impaired users. | 2024-11-10 | Khiem | Added audio feedback on controls, providing spoken confirmations for folding, brake engagement, and adjustments to accommodate visual impairments.